## Sheet1
GPU Enhanced LiDAR for Real Time 3D Sensing
Team Members: Amit Pachore (010317047) Bhupendra Naphade () Urvashi Agrawal (010702471) Anush Shankar (010652824) |  |  | Project Advisor: Dr. Harry Li
[6 empty] | Start Date: Aug 23, 2016 | End Date: May 13, 2016
Task Name | Task Owner | Start | End | Duration (days) | % Completion
Literature Survey for 3D Environment Sensing Techniques | Amit, Bhupendra, Anush, Urvashi | 2016-08-25 | 2016-09-15 | 21 | 100% |  |  | 21 | 0
Tester | Amit | 2016-08-25 | 2016-10-31 | 67 | 65.67% |  |  | 44 | 23
Tester | Bhupendra | 2016-11-01 | 2016-12-31 | 60 | 0% |  |  | 0 | 60
Tester | Urvashi | 2017-01-15 | 2017-03-14 | 58 | 0% |  |  | 0 | 58
Tester | Anush | 2017-03-15 | 2017-05-15 | 61 | 0% |  |  | 0 | 61
Install OpenCV on Hardware Platform | Amit, Bhupendra | 2016-08-25 | 2016-08-30 | 5 | 100% |  |  | 5 | 0
Run OpenCV Sample Programs on Hardware Platform | Anush, Urvashi | 2016-08-25 | 2016-08-30 | 5 | 100% |  |  | 5 | 0
Market Survey for USB Camera | Anush | 2016-08-25 | 2016-08-30 | 5 | 100% |  |  | 5 | 0
Interface RPLiDAR with Jetson | Amit, Bhupendra | 2016-08-30 | 2016-09-06 | 7 | 100% |  |  | 7 | 0
Draw 3D Axes using OpenCV | Anush, Urvashi | 2016-08-30 | 2016-09-06 | 7 | 100% |  |  | 7 | 0
Interface Servo Motor With Hardware | Amit, Bhupendra | 2016-08-30 | 2016-09-06 | 7 | 100% |  |  | 7 | 0
Write abstract of the Project | Amit, Bhupendra, Anush, Urvashi | 2016-08-30 | 2016-09-06 | 7 | 100% |  |  | 7 | 0
Prepare Project PPT | Bhupendra | 2016-09-06 | 2016-09-13 | 7 | 100% |  |  | 7 | 0
RPLiDAR Interface Report | Amit, Anush | 2016-09-06 | 2016-09-13 | 7 | 100% |  |  | 7 | 0
Draw 3D cube using OpenCV and 3D tranformation pipeline algorithm | Anush, Urvashi | 2016-09-06 | 2016-09-13 | 7 | 100% |  |  | 7 | 0
Github Respository Creation | Bupendra | 2016-09-13 | 2016-09-17 | 4 | 100% |  |  | 4 | 0
Capture Video and Images with OpenCV on Jetson | Urvashi | 2016-09-13 | 2016-09-20 | 7 | 100% |  |  | 7 | 0
Interface USB webcam with Jetson | Amit, Bhupendra | 2016-09-13 | 2016-09-20 | 7 | 100% |  |  | 7 | 0
Investigate PWM Drivers | Amit | 2016-09-13 | 2016-09-20 | 7 | 100% |  |  | 7 | 0
Final report first page, abstract and table of content | Anush | 2016-09-13 | 2016-09-20 | 7 | 100% |  |  | 7 | 0
PPT with Titile and Objecive | Anush | 2016-09-13 | 2016-09-20 | 7 | 100% |  |  | 7 | 0
Create a Frontal Plane along with 3D Cube | Anush, Amit | 2016-09-20 | 2016-09-27 | 7 | 100% |  |  | 7 | 0
Creae patch of image from captured image | Urvashi, Bhupendra | 2016-09-20 | 2016-09-27 | 7 | 100% |  |  | 7 | 0
Decorate the Frontal Plane with captured image and chess board pattern | Anush, Urvashi | 2016-09-27 | 2016-10-03 | 6 | 100% |  |  | 6 | 0
Get RPLIDAR readings and display on the frontal plane | Amit, Bhupendra | 2016-09-27 | 2016-10-03 | 6 | 20% |  |  | 1.2 | 4.8
Workbook 1 preparation | Amit, Bhupendra, Anush, Urvashi | 2016-10-03 | 2016-10-10 | 7 | 100% |  |  | 7 | 0
Implement OpenCV algorithms for parts of augmented reality module | Anush | 2016-10-10 | 2016-12-31 | 82 | 0% |  |  | 0 | 82
Implement OpenCV algorithms for parts of image processing | Urvashi | 2016-10-10 | 2016-12-31 | 82 | 0% |  |  | 0 | 82
Modify developed OpenCV algorithms to run on GPU architecture with CUDA programming | Amit | 2016-10-10 | 2016-12-31 | 82 | 0% |  |  | 0 | 82
Hardware Design for Prototype module | Bhupendra | 2016-10-10 | 2016-12-31 | 82 | 0% |  |  | 0 | 82
Workbook 2 preparation | Amit, Bhupendra, Anush, Urvashi | 2016-11-08 | 2016-11-15 | 7 | 0% |  |  | 0 | 7
Functional Spec prepparation | Amit, Bhupendra, Anush, Urvashi | 2016-11-08 | 2016-11-15 | 7 | 0% |  |  | 0 | 7
Report Part-A Preparation | Amit, Bhupendra, Anush, Urvashi | 2016-12-01 | 2016-12-08 | 7 | 0% |  |  | 0 | 7
Manufacture and Assemble the Prototype | Bhupendra | 2017-01-01 | 2017-02-28 | 58 | 0% |  |  | 0 | 58
Integrate the different modules of the Augmented Reality | Anush | 2017-01-01 | 2017-02-28 | 58 | 0% |  |  | 0 | 58
Integrate the different modules of the Image Processing for distance sensing | Urvashi | 2017-01-01 | 2017-02-28 | 58 | 0% |  |  | 0 | 58
Optimize AI and Image Processing algorithms for CUDA platform | Amit | 2017-01-01 | 2017-02-28 | 58 | 0% |  |  | 0 | 58
Integrared Program Testing and Bug Fixing | Amit, Bhupendra, Anush, Urvashi | 2017-03-01 | 2017-04-30 | 60 | 0% |  |  | 0 | 60
Project Part-B Report and Final Demo Preparation | Amit, Bhupendra, Anush, Urvashi | 2017-05-01 | 2017-05-13 | 12 | 0% |  |  | 0 | 12